## Slide 1: Project Integration Management SEII-Lecture 3
Dr. Muzafar Khan
Assistant Professor
Department of Computer Science
CIIT, Islamabad.

## Slide 2: Outline
Recap
Recent trends in IT projects
Project management process groups
Project Integration management

## Slide 3: Recap
Systems Philosophy
  Business, organization, technology
Organization frames
  Structure, HR, political, symbolic
Project life cycle
  Concept, development, implementation, close-out
IT projects are complex
Notes: Here is the outline for today’s lecture.

## Slide 4: Globalization [1/2]
Global village
Lower trade / political barriers
IT is the key enabler
Project managers need to address
  Communications
  Trust
  Common work practices
  Tools

## Slide 5: Globalization [2/2]
KPMG International suggestions after studying 600 global organizations
  Greater project discipline
  Think global, act local
  Collaboration over standardization
  Keep project momentum
  Use of newer and innovative tools

## Slide 6: Outsourcing
Acquiring goods/services from an outside source
Offshoring – another country
Reduced costs
Issues
  Integration and standardization of IT infrastructure and business processes
  Negotiating contracts, working plans, and managing virtual teams

## Slide 7: Virtual Teams
Remote locations
Same country / across the globe
Possible advantages
  Competitiveness, responsiveness, 24/7 availability
  Reduced costs, even no office space
  Work/life balance for team members
Possible disadvantages
  Isolating team members
  Communication problems
  Informal learning/networking
  Technology dependent

## Slide 8: Success Factors for Virtual Teams
Team processes
Leadership style
Trust and relationships
Team member selection and role preferences
Task-technology fit
Cultural differences
Computer-mediated communication
Team life cycles
Conflict management

## Slide 9: Project Management Process Groups [1/2]
Process
  A series of actions directed towards a specified goal
Project management – series of interlinked processes
Do not confuse it with project phases
Initiating processes
  Defining and authorizing project/phase
  At the beginning of each phase
Planning processes
  Devising and maintaining workable scheme
  Project management plan

## Slide 10: Project Management Process Groups [2/2]
Executing processes
  Coordinating people and other resources
  Development activities
Monitoring and closing processes
  Measuring and monitoring progress
  Corrective actions
Closing processes
  Formal acceptance
  Administrative activities

## Slide 11: Time Spent on Each Process Group
Figure source: IT Project Management, K. Schwalbe, 6th ed., p. 80

## Slide 12: Project Integration Management
Coordinating all knowledge areas throughout a project’s life cycle
Main processes
  Developing project charter
  Developing project management plan
  Directing and managing project execution
  Monitoring and controlling project work
  Performing integrated change control
  Closing project or phase

## Slide 13: Project Charter
A formal document to recognize the project
  Project title and date of authorization, contact info
  Project objectives, business need, justification
  Summary of project schedule, budget, communication plan
  Project success criteria
  Roles and responsibilities matrix
  Sign-off and comments sections

## Slide 14: Project Management Plan
To coordinate all project planning documents
Project planning assumptions and decisions
Assist in project’s execution and control
Baseline for progress measurement and project control
Dynamic, flexible, and subject to change
Information required from all knowledge areas
Main inputs: project charter, outputs from planning processes, enterprise environment factors
Main technique: Expert judgment

## Slide 15: Project Management Plan Contents [1/4]
Projects are unique so are management plans
Common sections
Introduction section
  Project title
  Brief project description
  Sponsor’s name
  Names of project manager and key team members
  Project deliverables
  List of reference material, definitions, and acronyms

## Slide 16: Project Management Plan Contents [2/4]
Organization section
  Organization charts
  Project responsibilities
  Other organizational / process-related information
Management and technical approaches
  Management objectives
  Project controls
  Risk management
  Project staffing
  Technical processes

## Slide 17: Project Management Plan Contents [3/4]
Scope management
  Major work packages
  Key deliverables
  Other work-related information
Schedule management
  Summary schedule
  Detailed schedule
  Other schedule-related information

## Slide 18: Project Management Plan Contents [4/4]
Budget section
  Summary budget
  Detailed budget
  Other budget-related information

## Slide 19: Directing and Managing Project Execution [1/2]
Main inputs: managing and performing the work as described in project management plan, and change requests
Most of the time spent on execution
Leading the team and managing stakeholders relationships
Project manager must be flexible and creative

## Slide 20: Directing and Managing Project Execution [2/2]
Coordinating planning and execution
  Those who will do the work should plan the work
Providing strong leadership
Providing a supportive culture
Capitalizing on product, business, and application area knowledge
Project execution tools and techniques
  Expert judgment and project management information systems

## Slide 21: Monitoring and Controlling Project Work
Changes are inevitable
90% of job: communicating and managing changes
Collecting, measuring, and disseminating performance information
Main inputs: project management plan and performance reports
Project management plan is the baseline for identifying and controlling changes
Main output: change request

## Slide 22: Performing Integrated Change Control [1/3]
Identifying, evaluating, and managing changes
Influencing the factors that create changes
Determine that a change has occurred
Managing actual changes as they occur
Main inputs: work performance information and change requests
Main outputs: updated change request status and project documents
Oral, written, formal, and informal change requests

## Slide 23: Performing Integrated Change Control [2/3]
Change control system
Change control board
Key stakeholders on the board
Configuration management
Proper communication
Possible drawbacks
  Time demanding
  48 hour policy

## Slide 24: Performing Integrated Change Control [3/3]
Table source: IT Project Management, K. Schwalbe, 6th ed., p. 164

## Slide 25: Closing Projects or Phases
Finalizing all the activities and transferring the completed / cancelled work
Main input: accepted deliverables
Main technique: expert judgment
Main output: final product, service, or result transmission, and process asset updates

## Slide 26: Summary
Recent trends in IT projects
  Globalization, outsourcing, and virtual teams
Project management process groups
  Initiating, planning, executing, monitoring and control, and closing processes
Project integration management
  Key processes and the relevant discussion