## Slide 1: Project Management Software Application PRM 705
Lecture 15

## Slide 2: Recap
Handshake with other MS Excel
Inserting customized column
Indicator column

## Slide 3: Today’s Outline
Creating WBS
Creating Milestone
Constraints and its types
Deadline
Resources

## Slide 4: Creating WBS

## Slide 5: Insert WBS Code

## Slide 6: Insert WBS Code

## Slide 7: 1. Creating a Milestone
Enter 0 days duration for a task, if you want to make it Milestone.

## Slide 8: 2. Creating a Milestone

## Slide 9: Constraints
Flexible constraints.
Moderate constraints.
Inflexible constraints.
A flexible constraint allows a task’s dates to change as the schedule changes. The default constraint, As Soon As Possible, is an example of a flexible constraint.
an inflexible constraint ties a task to a specific date. The Must Start On and Must Finish On constraints are the two inflexible constraints.
Between the flexible and inflexible constraints are moderate constraints. These constraints, such as Start No Earlier Than or Finish No Later Than

## Slide 11: Setting Constraints

## Slide 12: Deadlines
Suppose you want to keep a task deadline in mind but you don’t want to lock your schedule by setting an inflexible constraint. Instead, you can set a deadline.
Microsoft Project continues to update the schedule as needed, keeps track of deadline dates, shows them on the Gantt Chart, and displays a deadline indicator if a task finishes after its deadline.

## Slide 13: Setting Deadlines

## Slide 14: Thank You