## Slide 1: Project Management Software Application PRM 705
Lecture 16

## Slide 2: Recap
Creating WBS
WBS Numbering
Creating Milestone
Constraints and its types
Deadline

## Slide 3: Today’s Outline
Resources
Setting default currency
Cost Types
Resource units
Cost accrual
Resource Sheet

## Slide 4: What are Resources?
Resources are the people, equipment, and materials required to accomplish project tasks and goals.
There are two types of resources: work resources and material resources.
Work resources are the people and equipment that accomplish the work of a task.
Material resources are the consumable supplies that are used up in the performance on a task. Examples include concrete, steel, and soil.

## Slide 5: Working With Resources
Create a resource list
Set the calendars specifying the working days and times
Assign those resources to tasks.

## Slide 6: Changing Currency
File > Options

## Slide 7: Define Costing Unit

## Slide 8: Setting Cost
Variable costs: A variable cost depends on the time spent on assigned tasks. For example, suppose a resource is paid hourly (or weekly or monthly). The longer the resource spends on a task, the greater the resource cost will be for that task.
Fixed costs. A fixed cost remains constant regardless of the amount of time required to accomplish a task or the number of hours a resource spends on the task. For example, contractors often bid a fixed price for a job.
Per-use costs. A per-use cost is a flat usage charge you incur each time, and only each time, you use a resource. For example, the fee for renting a tractor might be $100 per use.

## Slide 9: Resource Assignment Units
When you assign a work resource or material resource to a task, you need to indicate how much of that resource is to be devoted to this assignment. The mechanism for doing this is the assignment unit. Normally done in percentage

## Slide 10: Control How Resource Cost Are Accrued
You can choose the point at which resource costs are incurred by setting the cost accrual for resources. Your accrual choices are:
  The entire cost at the start of an assignment.
  The entire cost at the end of an assignment.
  The prorated cost across the duration of the assignment as it progress

## Slide 11: Thank You