## Slide 1: Project Management Software Application PRM 705
Lecture 21

## Slide 2: Recap
Views
Inserting sub projects
Recurring tasks
Splitting Task
Adding Notes
Tracking

## Slide 3: Today’s Outline
Baseline
Set and save baseline
Update progress
Showing status line
Tracking Gantt Chart
Reporting

## Slide 4: Tracking
After you complete your plan, send final copy to your client for approval
After getting approval, save 3 or 4 copies at different locations (as backup)

## Slide 5: Baseline
As your project progresses, some tasks might take longer or shorter than planned Resources might cost more or less than you estimated.
To know whether all the actual mean you’re ahead of schedule or behind, within your budget or exceeding it, you need to be able to compare your actual schedule to some reference point.
That reference point is the baseline.

## Slide 6: Set & Save a baseline

## Slide 7: Update the Progress
Project > Update Project

## Slide 8: Show status line
Show status gridline
  Format > gridline > status date

## Slide 9: Changing view to tracking gantt chart
View > Gantt Chart > tracking Gantt Chart
View > zoom > entire project

## Slide 10: Insert a column for %age complete
Now you go to site and ask site in charge for actual progress

## Slide 11: Add columns actual start & actual finish
Use actual start and actual finish as per original progress
Use actual start and % complete as per original progress

## Slide 12: Baseline start & Baseline finish

## Slide 13: Insert a new bar in gantt chart
Format > Format > bar styles > Insert row

## Slide 14: How to modify legend in print preview

## Slide 15: How to modify legend in print preview
If you want to remove any of these from legend just place * in start of name of that bar in
  Format > Format > bar style

## Slide 16: Another baseline
You can create more then one baselines, infact 11 different baselines in MSP

## Slide 17: Reports

## Slide 18: Reports

## Slide 19: Report

## Slide 20: Customized Reports

## Slide 21: Customized Reports

## Slide 22: Visual Reports