## Slide 1: Project Management Software Application PRM 705
Lecture 30

## Slide 2: Recap
Responsible Manager
Activity Codes
Resources
Default Currency
Default Costing Unit
Material Unit
Resource Dictionary
Resource Assignment

## Slide 3: Today’s Outline
Creating resource dictionary
Resource assignment
Resource leveling
Milestones
Activity types
Resource curves
Customized curves
Cash flow
S curve

## Slide 4: Creating resource dictionary
OBS is organizational structure
Resources are people working on the project in actual
Role Vs Resource
  Chief Justice is role
  Iftikhar is resource
We can plan project based on roles or resorces

## Slide 5: Enter following resources

## Slide 6: Assigning resources to activities

## Slide 7: Assigning resources to activities
Now assign resources to your every activity.

## Slide 8: Resource Leveling

## Slide 9: Resource Leveling

## Slide 10: Resource Leveling
There may be problem in resource leveling if the resource calendar is different from activity / project calendar
In start of project add a general resource calendar and use it during project.

## Slide 11: Milestones
Start Milestone –This type is typically used to mark the beginning of a phase or to communicate project deliverables.
  Zero-duration activity
  Only has a start date
  You can assign a primary resource
  You cannot assign roles
Finish Milestone –This type is typically used to mark the end of a phase or to communicate project deliverables.
  Zero-duration activity
  Only has a finish date
  You can assign a primary resource
  You cannot assign roles

## Slide 12: Activity Types
The Activity Type determines whether the activity calendar or resource calendar is used during scheduling.
Resource dependent & task dependent
Task dependent is default
For effort driven (in activity details)

## Slide 13: Resource curves
Add a column for resource curve

## Slide 14: Adding your own customize curves

## Slide 15: Adding your own customize curves

## Slide 16: Cost usage – cash flow
Bottom layout > activity usage profile

## Slide 17: Cost usage – cash flow

## Slide 18: Cost usage – cash flow

## Slide 19: S-Curve

## Slide 20: Costing
Two types
  Direct
  Indirect (admin expenses etc)

## Slide 21: Thank You