## Slide 1: Project Management Software Application PRM 705
Lecture 32

## Slide 2: Complete Course Revision

## Slide 3: Course Recap
What is Project?
What is Project Management?
Importance of PM
Benefits of Project Management Tools
OBS, WBS & PBS

## Slide 4: Course Recap
Requirement gathering
WBS
WBS Dictionary
PBS
RAM
Resources
Dependency Types
Lag & Lead
Over-allocation
Resource Leveling

## Slide 5: Course Recap
Dependency Types
Lag & Lead
Over-allocation
Resource Leveling
Network diagram
CPM
Gantt Chart
Slack

## Slide 6: Course Recap
Lag & Lead
Network diagram
CPM
Gantt Chart
Slack

## Slide 7: Course Recap
Timeline
Different views
Setting Project Properties
Setting project information
Entering tasks
Working times
Calendars

## Slide 8: Course Recap
Network View
Setting project information
Changing Date Format
Automatic Schedule

## Slide 9: Course Recap
Adding new column
Linking tasks
Assigning calendar to multiple activities
Checking project total time
Entering durations

## Slide 10: Course Recap
Adding new column
Linking tasks
Assigning calendar to multiple activities
Checking project total time
Entering durations

## Slide 11: Course Recap
Task linking
Changing links
Adding Lag and Lead

## Slide 12: Course Recap
Changing Date format
Changing bar format
Putting data near bar
Identifying critical activities
Changing timescale

## Slide 13: Course Recap
Gridlines
Formatting summery bar
Critical Path on bars
Printing
Handshake with other MS Excel

## Slide 14: Course Recap
Inserting customized column
Indicator column
Creating WBS
WBS Codes

## Slide 15: Course Recap
Creating Milestone
Constraints and its types
Deadline
Resources

## Slide 16: Course Recap
Setting default currency
Cost Types
Resource units
Cost accrual
Resource Sheet

## Slide 17: Course Recap
Task types
Assignment units
Accrual at fix cost
Effort driven scheduling
Resource allocation
Changing resources

## Slide 18: Course Recap
Assignment units
Accrual at fix cost
Effort driven scheduling
Resource allocation

## Slide 19: Course Recap
Fixed Cost
Creating S-Curve
Tables
Grouping
Sorting
Filtering
Work contours

## Slide 20: Course Recap
Views
Inserting sub projects
Recurring tasks
Splitting Task
Adding Notes
Tracking
Baseline

## Slide 21: Course Recap
Baseline
Set and save baseline
Update progress
Showing status line
Tracking Gantt Chart
Reporting

## Slide 22: Course Recap
Intro to PV
History & Present
Oracle Primavera
Applications
Solution
Installation

## Slide 23: Course Recap
  EPS
  Creating new project
  Creating activities
  Toolbar
  Setting up column
  Bottom view

## Slide 24: Course Recap
  Calendar
  Applying calendar
  Durations column
  Entering durations
  Applying relationships

## Slide 25: Course Recap
Applying relationships
Automatic scheduling
Applying calendar to multiple activities
Checking project duration
Project Export
Project Import
Edit relationship
Finding Free slack

## Slide 26: Course Recap
Edit relationship
Finding Free slack
Date formatting
Bar formatting
Info near the bar
Bar legend
Customizing detailed layout
Changing row height and background color

## Slide 27: Course Recap
Another way of changing relationship
Row height
Background color
Progress spot light
Curtains
Timescale
printing

## Slide 28: Course Recap
WBS
Creating WBS Dictionary
Associating Activities to WBS
User defined fields
OBS
Activity Codes

## Slide 29: Course Recap
Resources
Default Currency
Default Costing Unit
Material Unit
Resource Dictionary
Resource Assignment

## Slide 30: Course Recap
Resource leveling
Milestones
Activity types
Resource curves
Customized curves
Cash flow
S curve

## Slide 31: Course Recap
Costing
Cost Accounts
Indirect costing
Tracking
  Milestones
  Baseline
  Update progress
  Activity % complete
  Progress using activity steps

## Slide 32: Thank You