## Slide 1: Project Management Software Application PRM 705
Lecture 4

## Slide 2: Recap
Requirement gathering
WBS
WBS Dictionary
PBS
RAM
Resources

## Slide 3: Today’s Outline
Dependency Types
Lag & Lead
Over-allocation
Resource Leveling
Network diagram
CPM
Gantt Chart
Slack

## Slide 4: Predecessor Task
A task (or activity) that must be started or finished before another task or milestone can be performed.

## Slide 5: Figure 6-3. Task Dependency Types

## Slide 6: Finish to Start
Finish to start (FS)
  A FS B = B can't start before A is finished, or in another words Activity A must be completed before Activity B can begin.
  (Foundations dug) FS (Concrete poured)

## Slide 7: Finish to Finish
Finish to finish (FF)
  A FF B = B can't finish before A is finished or in another words Activity A must be complete before Activity B can finish.[2]
  (Last chapter written) FF (Entire book written)

## Slide 8: Start to Start
Start to start (SS).
  A SS B = B can't start before A starts or in another words Activity B can start after Activity A has started.[2]
  (Project work started) SS (Project management activities started)

## Slide 9: Start to Finish
Start to finish (SF)
  A SF B = B can't finish before A starts
  (New shift started) SF (Previous shift finished)

## Slide 10: Leads & Lags

## Slide 11: Over Allocation
Over Allocation is when a project calls for more time than a team member has.

## Slide 12: Resource Leveling
To get the best performance and results from resources, you need to manage resource workloads to avoid over-allocations and under-allocations.

## Slide 13: Resource Leveling
Over Allocation can be solved by number of ways for example:
  Changing the relationships i.e. (SS, FS, SF, FF)
  Changing lag to “zero” or change it to lead
  Changing working time
  Changing Units
  Adding extra overtime hours to that particular resource

## Slide 14: Program Evaluation and Review Technique (PERT)
PERT is a network analysis technique used to estimate project duration when there is a high degree of uncertainty about the individual activity duration estimates.
PERT uses probabilistic time estimates:
  Duration estimates based on using optimistic, most likely, and pessimistic estimates of activity durations, or a three-point estimate.

## Slide 15: PERT Formula and Example
PERT weighted average =
  optimistic time + 4X most likely time + pessimistic time
  6
  Example:
  PERT weighted average =
  8 workdays + 4 X 10 workdays + 24 workdays = 12 days 6
  where:
  optimistic time= 8 days
  most likely time = 10 days
  pessimistic time = 24 days
  Therefore, you’d use 12 days on the network diagram instead of 10 when using PERT for the above example.

## Slide 16: Thank You